## Kaizen Overview of Phases
Phases of a Kaizen Event
“Kaizen workshops should be used to teach and make rapid changes. Kaizen workshop is a social invention that frees up a cross functional team to make changes in a week that otherwise can drag on for months.
Selection of right people is key
Experienced facilitator needs to have a deep understanding of lean tools & philosophy with a specific problem to tackle.
Kaizen workshop should not become an end in and of itself.
Kaizen workshops best used as 1 tool to implement specific improvements guided by a future state value stream map.”
The Toyota Way: 14 Management Principles from the World’s greatest manufacturer. Jeffrey K. Liker . Mc-Graw Hill. 2004. p.304

## Checksheet for Phase I
Phase One – Checklist OK TO PROCEED
Champion identified & committed to the project
Champion agrees to kick-off the lean event
Champion agrees to support final recommendations
Readiness reviews have been completed with Champion/Sponsor/Facilitator
Project officially approved
Clear Scope has been established
AS-IS value stream map has been created
Baseline cycle time metrics are clearly understood
Key Target areas have been identified
Cycle time targets and project timelines established
Required sub-matter experts are available for the event
All key decision makers have been identified & included
Resources have been allocated & work prioritized
Post event reviews have been scheduled
Determine stakeholders/leader(s) – CHAMPION(s) who support the event & its output
Define Scope & Set Objectives with champion(s)
Create preliminary current state map and problem statement
Collect all relevant documents & data
  Consider posting a preliminary current state map in the team room
Determine required participants
Obtain agreement from sponsor to ensure participants can attend
Review objectives, agenda and time requirements with your champion, sponsor and facilitators
Send invitation and work with all participants to manage time conflicts and other issues with participation.
Prework Required During Phase One

## Lean Board for Phase II
Lean Board
Example of metrics that could be used
Metric | Unit of Measure | Baseline | Target | Current | % Improved | Owner
Lead Time | Days
Delivery | % on time
Quality | Defects per Million Opportunities
Productivity | Hours per project
Cycle Time | Days

## Format for Phase II
Monday
Current process
Walk the process w/ real examples – GO TO GEMBA
Capture data – as is
Analyze cycle time and value adding
Identify DOWNTIME waste(s)
Waste elimination
Root cause analysis & brainstorming
Lean tools/techniques
Future State mapping
Taking action
Design new process
Implement changes
Document standards/procedures
Train employees
Review
Prepare and conduct stakeholder presentation
30 day action plan for required actions
Recognize & Celebrate!
Tuesday
Wednesday
Thursday
Friday

## Phase III Kaizen Newspaper
Kaizen Newspaper, Project Name |  |  |  |  | Status Legend | Not Started | In Progress | On Hold
Latest report-out date, x/x/20xx | [5 empty] | Completed | Road Block | Deleted
Action Plan | [5 empty] | Action Item Tracking | [5 empty] | Attendees listed | B.Donovan, L. Kirmshoff, F. Barnes, H. White | B.Donovan, L. Kirmshoff, F. Barnes, H. White, C.Mapa, B.Toldt
Category | SubCategory | Item | Area within Sub-Category | Action | Owner | Team members | Timing | Overall Status | Start Date | Target Complete Date | Late? | Actual Complete Date | Status week of 1/11 | Status Week of 1/18
| TOPIC ONE | 1
TOPIC ONE | Sub topic | 1.0 | Weekly Status/Project Update calls | set up weekly calls w/CLOUD Team; Tuesdays 1-2:30 EST. | A.Cardinal | k. shel, f. noon | 1 | Completed | 2016-01-01 | 2016-01-02 |  | 2016-01-03 | Calls set up for wednesdays 4 pm
TOPIC ONE | Sub topic | 1.1 | To Be process | Develop process map of 'to be' proposed process & review w/sponsors/leaders | H.Lare | K.Shelf | 7 | In Progress | 2016-01-06 | 2016-01-13 | YES |  | Map underway - still validating w/Sponsors
TOPIC ONE | Sub topic | 1.2 | To Be process | Develop process map of 'to be' proposed process & review w/Apu | M.Thompson | A.insta | 9 | Completed | 2016-01-19 | 2016-01-28 |  | 2016-01-20 | Map reviwed and approved
TOPIC ONE | Sub topic | 1.3 | Amazon - To Be process | Ask AWS if they can provide discount file at the UAI level. | B.Hemphill | N.Dana | 60 | Deleted |  |  |  |  | Impossible - validated w/AAWS
TOPIC ONE | Sub topic | 1.4 | Amazon | Work w/Amazon to ensure Discount File is sent consistently by the 7th of the month | K.Malone | J.Stewart,N.Malone,C.Fist | 14 | On Hold | 2016-01-10 | 2016-01-24 |  | 2016-01-20 | Asked them to do this, they said they will try - unable to confirm or test.
| TOPIC TWO | 2.0
TOPIC TWO | Sub topic | 2.0 | Weekly Status/Project Update calls | set up weekly calls w/Technology Team; Fridays 1-2:00 EST. | C.Mapa | G.Leornado | 1 | Completed | 2016-02-02 | 2016-02-03 |  | 2016-02-01 | Set up for Thursdays 8 AM
TOPIC TWO | Sub topic | 2.1 | Source of Truth | Determine Source of truth for End Point Security. S | G.Dinsel | F.Fox | 5 | Road Block | 2015-12-15 | 2015-12-20 |  | 2015-12-21 | Product owner has no idea how to find source of truth
TOPIC TWO | Sub topic | 2.2 | Source of Truth | Determine Source of truth for Identify & Access Management - where do we get a list of SSO ID's to be billed? | H.Hedway | F.Kettal | 5 | Completed | 2016-12-20 | 2016-12-25 |  | 2016-12-22
TOPIC TWO | Sub topic | 2.3 | Source of Truth | Once IDM is confirmed (see above action) - set up meeting w/Billing lead to determine method for automated file send to billing process w/the list of SSO's to be billed for this. | O.Obderwal | J.Jein | 14 | In Progress | 2016-01-15 | 2016-01-29 | YES |  | working to set this up
| TOPIC THREE | 3.0
TOPIC THREE | Sub topic | 3.0 | Weekly Status/Project Update calls | set up weekly calls w/Technology Solutions; Thursdays 1 PM EST, beginning 8/20/15. | H.Katz | L.Pressly, R.Hindeman | 1 | In Progress | 2016-02-03 | 2016-02-04 |  | 2016-03-03
TOPIC THREE | Sub topic | 3.1 | As Is Process | Confirm with Finance current process & agree to "TO BE" to G2G_Manual upload from Product Owner | K.Lowell | R.Handick | 3 | In Progress | 2016-01-16 | 2016-01-19 |  | 2016-01-28 | Have asked product owner to sign off
TOPIC THREE | Sub topic | 3.3 | As Is Process | Confirm with Finance current process & agree to "TO BE" to G2G_SSO 3 as training is SSO based | A.Mukta | C.Clarke | 19 | In Progress | 2016-01-29 | 2016-02-17 |  | 2016-02-18 | Have asked finance to sign off.
Formulas:
Target Complete Date = IF(AND([Start Date]>0,[In Progress]>0),[Start Date]+[In Progress],"")
Late? = IF(AND([Actual Complete Date]="",[Target Complete Date]<TODAY()),"YES","")