## Actions and Status Updates
Action Plan Tracking Newspaper
Initiative Name |  |  |  | Status Legend
Project Name |  |  |  | Road Block | Not Started | In Progress | On Hold | Cancelled | Completed |  | Attendees: | Susan, Leader 1, Leader 2, Leader 3 | Leila, Susan, Leader 1, Leader 2, Leader 3
Date of Last Update
Category | SubCategory | Item | Action | Owner | Team members | Timing (duration calendar days) | Overall Status (enter status to update color) | Start Date | Target Complete Date | Tracking behind? | Actual Complete Date | Status 2/12 | Status 2/20
Project Pulsing |  | 1
Project Pulsing | Projects | 1.1 | Action 1 | Leader 2 | OPEX team | 15 | Completed | 2020-02-12 | 2020-02-27 |  | 2020-02-26 | Susan agreed to take Kaizen & all pitches and put into one presentation | Team to provide input by Friday EOB
Project Pulsing | Quick Hits | 1.2 | Action 2 | Leader 2 | Frank, Paul |  | In Progress | 2020-01-20 | 2020-02-04 | YES
OPEX team |  | 2
OPEX team | PC's | 2.1 | Get OPEX team same PC's | Leader 2 | Rhonda | 20 | Completed | 2020-02-03 | 2020-02-23 | YES | 2020-02-28 | PC's ordered | PC's being updated.
Green Belts |  | 3
Green Belts | Wave I GBs | 3.1 | Green Belt Awards Ceremony - best of '20 | Leader 2 | Jose, Luis and Kim |  | On Hold | 2020-01-20 | 2020-02-28 |  |  | Meeting w/Fran to discuss 2/13
Green Belts | Wave I GBs | 3.2 | Green belts with Company Logo and Name embroidered & Certificate | Leader 2 | Alan | 25 | Cancelled
Standard Templates & Tools |  | 4
Standard Templates & Tools | Site Assessment | 4.1 | Site Assessment finalize format with rating scale by Process | Leader 1 | OPEX team | 35 | In Progress | 2020-01-24 | 2020-02-28 | YES |  | Review next Monday in team meeting | Team bought off - Documenting in Confluence.
Standard Templates & Tools | Site Assessment | 4.2 | Propose GEMBA walk format to plant and operations leadership | Leader 2 | Operations Team |  | Not Started
Formulas:
Completed = IF(AND([Cancelled]>0,[In Progress]>0),[Cancelled]+[In Progress],"")
Tracking behind? = IF([Completed]="","",IF(OR(AND([On Hold]="In Progress",[Completed]<TODAY()),[Attendees:]>[Completed]),"YES",""))