## Instructions
Instructions
1 | Use the Kaizen Checklist to plan for the event; 3 weeks prior, 1 week prior and during the event. Check off items as you secure them. Use the comments section to add detail for each item to keep a record of decisions made.
2 | Use the Proposed Agenda to create the agenda for your Kaizen - add additional sheets if your Kaizen is for multiple days. Make sure to include icebreakers, sponsor reviews at the end of the day or week, breaks every 2 hrs and an opportunity at the end of the event for the participants to provide feedback. If you input duration (in minutes) and the first topics' start time, the rest of the cells will calculate automatically for you.
3 | On the day/week of the Kaizen event, use the detailed action planner to document the agreed up actions, post-Kaizen.
4 | To advertise the results with stakeholders, use the shortened version of the Newspaper. This provides the information in a summary level and easy to digest manner.
5 | Use the Kaizen event scorecard to document the metrics you will use to measure success. Make sure during the Kaizen (or prior) to gather the baseline performance. Then continue to measure and document results at intervals after the Kaizen Event.
6 | For the team, use the detailed action plan and continue to monitor these actions for 30 days. Provide a formal 60, 90, 120 day review post-Kaizen in order to ensure items are closed out on timely basis.
7 | Certain cells automatically calculate and formulate. All you need to do is enter status in the options given and the cell will format correctly.
8 | The % actions complete will automatically calculate - you do not need to override the cells to accomplish this.

## Kaizen Checklist
Kaizen Event - Checklist
Checklist Item | Phase | Timing | Activity | Additional Notes | Status | Comments | Status Key
1 | 1: Preparation | 3 weeks prior | Define the scope & set objective(s) with champion(s) | Make sure scope is doable in the timeframe you have |  |  | Complete
2 |  |  | Determine stakeholder(s), leader(s), champion(s) who will support the event & its output |  |  |  | Delayed
3 |  |  | Project/Kaizen Event officially approved |  |  |  | In-Progress
4 |  |  | Create preliminary current state map and problem statement |  |  |  | Road Block
5 |  |  | Determine required participants |  |  |  | Not Started
6 |  |  | Identify required documents & data and develop action plan to gather all of this. |  |  |  | Not 30 Day Action
7 |  |  | Create proposed agenda for Kaizen | Include Training as well as Data review, problem solving and action planning |  |  | Deleted
8 |  |  | Review objectives, agenda and time requirements with your champion, sponsor and facilitators
9 |  |  | Obtain agreement from sponsor(s) to ensure core team participants can attend 100% of the time | It's critical that participants are available 100% of time - no IN/OUT participation unless as an SME
10 |  |  | Send invitation and work with all participants to manage time conflicts and other issues with participation
11 |  |  | Send invitation for end of the day to the Champion/sponsor and key stakeholders. | Typically 15 min at end of day to solve problems/approve solutions and at the end of the Kaizen to review progress/changes and approve
12 |  |  | Secure room(s)/space for the event and confirm date(s). | Located as close as possible to the process area being reviewed. Available for duration of event.
13 |  |  | Analyze data gathered; prepare for review with champion/sponsor and then for use during the Kaizen
14 | 1: Preparation | 1 week prior | Review data gathered with facilitator, champion and sponsor
15 |  |  | Champion confirms commitment to kick-off the lean event
16 |  |  | Champion agrees to support final recommendations
17 |  |  | Prepare Kaizen Participation package with all required data, agendas, scope and objectives.
18 |  |  | Gather required supplies, post it's self stick easel pads, flip charts and markers, projector, training materials, catering requirements, snacks, icebreaker supplies | Quick icebreaker each morning before start of day
19 |  |  | Readiness reviews have been completed with Champion/Sponsor/Facilitator
20 |  |  | “As-is” value stream or process map finalized & placed in room | Process boundaries, customers, suppliers clearly identified
21 |  |  | Baseline metrics are clearly understood
22 |  |  | Key Target areas have been identified
23 |  |  | Required sub-matter experts are available for the event
24 |  |  | All key decision makers have been identified & included
25 |  |  | Resources have been allocated & work prioritized | Some SME's could be required for specific parts of the Kaizen, not the entire time.
26 |  |  | Post-event reviews have been scheduled
27 | 2: Kaizen Event | Day 1 or Part 1 | Walk the process w/ real examples – GO TO GEMBA
28 |  |  | Capture data "As Is"
29 |  |  | Analyze cycle time and value adding
30 |  | Day 2 or Part 2 | Identify DOWNTIME waste(s)
31 |  |  | Waste Elimination: Root cause analysis & brainstorming
32 |  |  | Waste Elimination: Lean tools/techniques
33 |  |  | Future State mapping
34 |  | Days 3-4 or Part 3 | Taking Action: Design new process
35 |  |  | Taking Action: Implement Changes
36 |  |  | Taking Action: Document standards/procedures
37 |  |  | Taking Action: Train Employees
38 |  | Days 4-5 or Part 4 | Prepare and conduct stakeholder presentation
39 |  |  | 30 day action plan for required actions
40 |  |  | Kaizen Event Scorecard/Dashboard | Prepare dashboard to share results achieved
41 |  |  | Recognize & Celebrate! | Try to give the team the last afternoon off as these events are usually grueling and go well beyond the 8 hr work day.

## Proposed Agenda
Kaizen Event Agenda
Project Name
Project Scope
Project Objective
Lean Leader
Project Sponsor
Project Champion
Date of Event
Location
Participants
Lead/Facilitator | Start Time | End Time | Duration | Topic/Objectives | Comments
| 9:00 | 10:00 | 1:00
| 10:00 | 12:00 | 2:00
| 12:00 | 12:30 | 0:30
| 12:30 | 13:30 | 1:00
| 13:30 | 15:30 | 2:00
| 15:30 | 16:30 | 1:00
| 16:30 | 17:00 | 0:30

## Newspaper
Kaizen Newspaper
# | Item | Owner | Date | Month1 | Month2 | Month3 | Month4 | Status Key
1 | [7 empty] | Complete
2 | [7 empty] | Delayed
3 | [7 empty] | In-Progress
4 | [7 empty] | Road Block
6 | [7 empty] | Not Started
30 Day Review | [7 empty] | Not 30 Day Action
60 Day Review | [7 empty] | Deleted
90 Day Review

## Detailed Act Plan
Detailed Action Plan
Project Name
| Date of Kaizen Event | 2025-02-03
| Target Completion Date for all actions | 2025-03-05
| Status | Count | Completion %
| Complete | 0
| Delayed | 0
| In-Progress | 0
| Road Block | 0
| Not Started | 0
| Not 30 Day Action | 0 | Types of Action
| Deleted | 0 | CapEx | OpEx | Just Do It | Other
| Total Number of Actions | 0
# | Action | Resp. | Due Date | Type of Action | Actual Completion Date | Status | Comment
1 |  |  | 2025-03-05
2 |  |  | 2025-03-05
3 |  |  | 2025-03-05
4 |  |  | 2025-03-05
5 |  |  | 2025-03-05
6 |  |  | 2025-03-05
7 |  |  | 2025-03-05
8 |  |  | 2025-03-05
9 |  |  | 2025-03-05
10 |  |  | 2025-03-05
11 |  |  | 2025-03-05
12 |  |  | 2025-03-05
13 |  |  | 2025-03-05
14 |  |  | 2025-03-05
15 |  |  | 2025-03-05
16 |  |  | 2025-03-05
17 |  |  | 2025-03-05
18 |  |  | 2025-03-05
19 |  |  | 2025-03-05
20 |  |  | 2025-03-05

## Detailed Act Plan Example
Detailed Action Plan Example
Name of Kaizen Event: Imprpve Pour Line #2 Attainment in factory XYZ
| Date of Kaizen Event | 2025-02-03
| Target Completion Date for all actions | 2025-03-05
| Status | Count | Completion % | 50%
| Complete | 9
| Delayed | 0
| In-Progress | 7
| Road Block | 0
| Not Started | 2
| Not 30 Day Action | 2 | Types of Action
| Deleted | 0 | CapEx | OpEx | Just Do It | Other
| Total Number of Actions | 20
# | Action | Resp. | Due Date | Type of Action | Actual Completion Date | Status | Comment
1 | Start weekly shift change-over meetings between the PPX pour line and the 2nd shift bun cut line | Matt W/ Jacob H | 2025-03-05 | JDI |  | In-Progress | Meetings will be used a communication point between shifts 2/26: commincationstarted follow-up 3/2 to formalize
2 | CSRs to ask customers if the would like to order full bun when they order short buns | Stephannie G | 2025-03-05 | JDI | 2020-02-26 | Complete | 2/26: need to place on the control plan
3 | Create consumption book | Brad T/ Tammy N | 2025-03-05 | JDI |  | In-Progress
4 | Remeasure 0033625618 | Sam J | 2025-03-05 | JDI | 2020-02-07 | Complete | Floor Exercise
5 | Measure high production mover at the NBC | Samantha | 2025-03-05 | JDI | 2020-02-07 | Complete | Floor Exercise
6 | Measure high production mover at the EBC | Keith/ Joe | 2025-03-05 | JDI | 2020-02-07 | Complete | Floor Exercise
7 | See production request for high moving measured by team | Sam J | 2025-03-05 | JDI | 2020-02-26 | Complete | Floor Exercise
8 | Ensure operators are measuring materials correctly | Team | 2025-03-05 | JDI | 2020-02-07 | Complete | Floor Exercise
9 | Install LED lighting the foam tunnel to ensure pourline personnel can see their product clearly | Justin B | 2025-03-05 | JDI |  | In-Progress | 2/26: JH to be submitted by 2/28
10 | Verify distance measurement to ensure we are accurately measuring materials | Jacob H | 2025-03-05 | JDI |  | In-Progress | 2/26: Team to take measurments Pythagorean theorem, should be used to determine if the straight line measurement is correct with for measuring slope material
11 | Compare demand vs actual | Tammie N/ Brad T | 2025-03-05 | JDI | 2020-02-26 | Complete | 2/26: done daily
12 | Remeasure loaf after the bun has fully cured | Jacob H/ Matt W | 2025-03-05 | JDI |  | In-Progress | 2/26: Underway via NBC
13 | Use shrinkage measurements to determine a shrinkage equation for PPX grades | Jacob H | 2025-03-05 | JDI |  | Not Started | 2/26: above action must me completed priro to moving with this Equation Will ensure that the correct amounts are produced
14 | Install new automatic measuring light (Keyence device) | Engineering | 2025-03-05 | CAPEX |  | Not 30 Day Action | Operator is currently manually reading this measurement it would be value add to remove the human error from this process
15 | Verify Ticketed dimensions prior to cutting material | Matt W/ Jacob H | 2025-03-05 | JDI |  | In-Progress | If measurement match operators are free to cut the material to the order, if not pour line personnel should be notified
16 | Ensure operator is down grading correctly | Team | 2025-03-05 | JDI | 2020-02-20 | Complete | 2/26: During NBC Event team found that this wasn t being completed correctly and agreed to downgrade 1" on everything including WIP buns
17 | Install cameras to replace mirrors | Engineering | 2025-03-05 | CAPEX |  | Not 30 Day Action | 2/26: On Hold until JH talks with personel Mirrors are dirty and operators struggle to use them
18 | Align bun at face of bun room and add floor marker for measuring | Jacob H | 2025-03-05 | JDI |  | In-Progress | 2/26: Vet out if we have the devices in place to stop ever bun in the same spot. The will create MUV if bun are cured while hanging.
19 | Calibrate footage Counter | Derek | 2025-03-05 | JDI |  | Not Started
20 | For the calendar dates 2/3- 2/11. Compare ticketed, to SAP to poured amounts | Brad T | 2025-03-05 | JDI | 2020-02-26 | Complete | Brad will review with PL team for next steps

## Kaizen Event Scorecard
Kaizen Event Scorecard
The Kaizen Event Scorecard conveys improvement results. It provides the team with necessary data to make corrections on negative trends if improvements are not going as expected. The scorecard provides Management with progress-to-date.
Name of Kaizen Event |  |  |  | Site/Location |  |  | Date
Value stream impacted |  |  |  | Process Owner(s) |  |  | Team Members
Team Champion/sponsor |  |  |  | Team Leader
METRICS
MEASUREMENTS | # Start of Event | #End of Event | 7 Day Date: | 14 Day Date: | 30 Day: Date | 60 Day Date: | 90 Day Date: | 6 months Date: | Target
Overall Evaluation: R/Y/G
Green - performance meets target
Yellow - Performance is short but close to Taret (within 10% of target)
Red - Performance is significantly unvaborable to target (below 10% of target)
If a measurement is not meeting the target, use the below 4 W's (what, who when and why) to clearly indicate how you plan to meet or exceed target.
What | Who | When | Why
Comments/Notes